## All HEIs (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3
HEI |  | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Required funds October - December 2016 | Reasons for slow progress (if any)
|  | Rs. Mn | Rs. Mn | % | Rs. Mn | Rs. Mn | Rs. Mn
|  | (a) | (b) | ( c) | (d) | (e) | (f)
(d) + ( e)
1 | PDN | 1263 | 630.08 | 49.8876 | 158.06 | 424.17 | 582.23 |  | 50.69
2 | CMB | 787 | 303.01 | 38.5019 | 142.95 | 341.04 | 483.99 |  | 0
3 | SJP | 2621 | 817 | 31.1713 | 247 | 1357 | 1604 |  | 200
4 | KLN | 1251 | 302.44 | 24.1759 | 200.59 | 352.04 | 552.63 |  | 395.93
5 | MRT | 1545 | 816.03 | 52.8175 | 313 | 310.42 | 623.42 |  | 105.55
6 | UJA | 2417 | 851.2 | 35.2172 | 107.1 | 1450.2 | 1557.3 |  | 8.5
7 | RUH | 1409 | 593.36 | 42.1121 | 636.71 | 180 | 816.71 |  | -1.07
8 | OUSL | 230 | 88.05 | 38.2826
9 | EUSL | 753 | 436.3 | 57.9416 | 34 | 51.2 | 85.2 |  | 231.5
10 | RUSL | 1147 | 387.98 | 33.8256 | 380 | 296 | 676 |  | 83.02
11 | SUSL | 870 | 106.26 | 12.2138 | 266.91 | 205.99 | 472.9 |  | 290.84
12 | SEUSL | 702 | 165.51 | 23.5769 | 348.8 | 187.69 | 536.49 |  | 0
13 | WUSL | 1416 | 404.68 | 28.5791 | 180.1 | 419.33 | 599.43 |  | 411.89
14 | UVPA | 421 | 182.63 | 43.38 | 112 | 125.97 | 237.97 |  | 0.4
15 | UWU | 825 | 160.58 | 19.4642 | 134.796 | 186.056 | 320.852 |  | 343.568
16 | Trinco | 515 | 318.38 | 61.8214 | 97.35 | 99.27 | 196.62 |  | 0
17 | Other Postgraduate Institutes | 73 | 42.83 | 58.6712
18 | Other Higher Educational Institutes | 730 | 320.98 | 43.9699
19 | PGIM | 435 | 74 | 17.0115 | 168 | 145.6 | 313.6 |  | 47.4
20 | UGC | 1232 | 160.13 | 12.9976 |  |  |  |  | 1071.87
Total |  | 20642 | 7161.43 | 34.6935 | 3527.366 | 6131.976 | 9659.342 |  | 3821.228
Innitial Allocation |  | 15942 |  |  | Innitial Allocation |  | 15942 | 15942
Technology Stream |  | 3000 |  |  | Technology Stream |  | 3000 | 3000
Establishment of Engineering Faculties |  | 1200 |  |  | Establishment of Engineering Faculties |  | 400 | 1200
Staff Quarters |  | 300 |  |  | Staff Quarters |  | 150 | 300
Medical Faculty |  | 200
Total Allocation |  | 20642 |  |  | Total Allocation |  | 19492 | 20442

## Adjusted Summary All HEIs (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3 | [7 empty] | Rs. Million
| HEI | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 % | Committed Expenditure up to 30.09.2016 | with Committed Expenditure % | Target Expenditure October - December 2016 | With Target Expenditure % | Reasons for slow progress (if any)
1 | PDN | 1263 | 630.08 | 49.8876 | 158.06 | 62.4022 | 424.17 | 95.9865 |  | 50.69
2 | CMB | 787 | 303.01 | 38.5019 | 142.95 | 56.6658 | 341.04 | 100 |  | 0 | 445.96
3 | SJP | 2621 | 817 | 31.1713 | 247 | 40.5952 | 1357 | 92.3693 |  | 200 | 0.56666
4 | KLN | 1251 | 302.44 | 24.1759 | 200.59 | 40.2102 | 352.04 | 68.3509 |  | 395.93 | 56.6658
5 | MRT | 1545 | 816.03 | 52.8175 | 313 | 73.0764 | 310.42 | 93.1683 |  | 105.55
6 | UJA | 2417 | 851.2 | 35.2172 | 107.1 | 39.6483 | 1450.2 | 99.6483 |  | 8.5
7 | RUH | 1409 | 593.36 | 42.1121 | 636.71 | 87.3009 | 180 | 100.0759 |  | -1.07
| OUSL | 230 | 88 | 38.2609 |  | 38.2609 |  | 38.2609
8 | EUSL | 753 | 436.3 | 57.9416 | 34 | 62.4568 | 51.2 | 69.2563 |  | 231.5
9 | RUSL | 1147 | 387.98 | 33.8256 | 380 | 66.9555 | 296 | 92.762 |  | 83.02
10 | SUSL | 870 | 106.26 | 12.2138 | 266.91 | 42.8931 | 205.99 | 66.5701 |  | 290.84
11 | SEUSL | 702 | 165.51 | 23.5769 | 348.8 | 73.2635 | 187.69 | 100 |  | 0
12 | WUSL | 1416 | 404.68 | 28.5791 | 180.1 | 41.298 | 419.33 | 70.9117 |  | 411.89
13 | UVPA | 421 | 182.63 | 43.38 | 112 | 69.9834 | 125.97 | 99.905 |  | 0.4
14 | UWU | 825 | 160.58 | 19.4642 | 134.796 | 35.8032 | 186.056 | 58.3554 |  | 343.568
15 | Trinco | 515 | 318.38 | 61.8214 | 97.35 | 80.7243 | 99.27 | 100 |  | 0
17 | Other Postgraduate Institutes | 73 | 43 | 58.9041 |  | 58.9041 |  | 58.9041
18 | Other Higher Educational Institutes | 730 | 321 | 43.9726 |  | 43.9726 |  | 43.9726
19 | PGIM | 435 | 74 | 17.0115 | 168 | 55.6322 | 146 | 89.1954
20 | UGC | 1232 | 160 | 12.987 |  | 12.987 |  | 12.987
Total |  | 20642 | 7161.44 | 34.6935 | 3527.366 | 51.7818 | 6132.376 | 81.4901 |  | 3820.818

## Summary Final (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3 | [8 empty] | Rs. Million
| HEI | Form | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 % | Committed Expenditure up to 30.09.2016 | with Committed Expenditure % | Target Expenditure October - December 2016 | With Target Expenditure % | Reasons for slow progress (if any)
1 | PDN |  | 1263 | 630.08 | 49.8876 | 158.06 | 62.4022 | 424.17 | 95.9865 |  | 50.69
2 | CMB |  | 787 | 303.01 | 38.5019 | 142.95 | 56.6658 | 341.04 | 100 |  | 0 | 445.96
3 | SJP |  | 2621 | 817 | 31.1713 | 247 | 40.5952 | 1357 | 92.3693 |  | 200 | 0.56666
4 | KLN |  | 1251 | 302.44 | 24.1759 | 200.59 | 40.2102 | 352.04 | 68.3509 |  | 395.93 | 56.6658
5 | MRT |  | 1545 | 816.03 | 52.8175 | 313 | 73.0764 | 310.42 | 93.1683 |  | 105.55
6 | UJA |  | 2417 | 851.2 | 35.2172 | 107.1 | 39.6483 | 1450.2 | 99.6483 |  | 8.5
7 | RUH |  | 1409 | 593.36 | 42.1121 | 796.71 | 98.6565 | 20 | 100.0759 |  | -1.07
8 | EUSL |  | 753 | 436.3 | 57.9416 | 34 | 62.4568 | 51.2 | 69.2563 |  | 231.5
9 | RUSL |  | 1147 | 387.98 | 33.8256 | 380 | 66.9555 | 296 | 92.762 |  | 83.02
10 | SUSL |  | 870 | 106.26 | 12.2138 | 266.91 | 42.8931 | 205.99 | 66.5701 |  | 290.84
11 | SEUSL |  | 702 | 165.51 | 23.5769 | 348.8 | 73.2635 | 187.69 | 100 |  | 0
12 | WUSL |  | 1216 | 404.68 | 33.2796 | 180.1 | 48.0905 | 419.33 | 82.5748 |  | 211.89
13 | UVPA |  | 421 | 182.63 | 43.38 | 112 | 69.9834 | 125.97 | 99.905 |  | 0.4
14 | UWU |  | 825 | 160.58 | 19.4642 | 134.796 | 35.8032 | 186.056 | 58.3554 |  | 343.568
15 | Trinco |  | 515 | 318.38 | 61.8214 | 97.35 | 80.7243 | 99.27 | 100 |  | 0
16 | PGIM |  | 435 | 74 | 17.0115 | 168 | 55.6322 | 145.6 | 89.1034 |  | 47.4
17 | PGIPBS |  | 510 | 1.84 | 0.36078 | 3.62 | 1.0706 | 4.54 | 1.9608 |  | 500
18 | IIM |  | 157 | 34.7 | 22.1019 | 0 | 22.1019 | 122.3 | 100 |  | 0
19 | GWAI |  | 164 | 43.66 | 26.622 | 90.38 | 81.7317 | 29.5 | 99.7195 |  | 0.46
Total |  |  | 19008 | 6629.64 | 34.8782 | 3781.366 | 54.7717 | 6128.316 | 87.0124 |  | 2468.678

## Summary (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3 | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | PDN |  | 1263 | 630.08 | 49.89% | 158.06 | 424.17 |  | 50.69
2 | CMB |  | 787 | 303.01 | 38.5% | 142.95 | 341.04 |  | 0
3 | SJP |  | 2621 | 817 | 31.17% | 247 | 1357 |  | 200
4 | KLN |  | 1251 | 302.44 | 24.18% | 200.59 | 352.04 |  | 395.93
5 | MRT |  | 1545 | 816.03 | 52.82% | 313 | 310.42 |  | 105.55
6 | UJA |  | 2417 | 851.2 | 35.22% | 107.1 | 1450.2 |  | 8.5
7 | RUH |  | 1409 | 593.36 | 42.11% | 796.71 | 20 |  | -1.07
8 | EUSL |  | 753 | 436.3 | 57.94% | 34 | 51.2 |  | 231.5
9 | RUSL |  | 1147 | 387.98 | 33.83% | 380 | 296 |  | 83.02
10 | SUSL |  | 870 | 106.26 | 12.21% | 266.91 | 205.99 |  | 290.84
11 | SEUSL |  | 702 | 165.51 | 23.58% | 348.8 | 187.69 |  | 0
12 | WUSL |  | 1216 | 404.68 | 33.28% | 180.1 | 419.33 |  | 211.89
13 | UVPA |  | 421 | 182.63 | 43.38% | 112 | 125.97 |  | 0.4
14 | UWU |  | 825 | 160.58 | 19.46% | 134.796 | 186.056 |  | 343.568
15 | Trinco |  | 515 | 318.38 | 61.82% | 97.35 | 99.27 |  | 0
16 | PGIM |  | 435 | 74 | 17.01% | 168 | 145.6 |  | 47.4
17 | PGIPBS |  | 510 | 1.84 | 0.3608% | 3.62 | 4.54 |  | 500
18 | IIM |  | 157 | 34.7 | 22.1% | 0 | 122.3 |  | 0
19 | GWAI |  | 164 | 43.66 | 26.62% | 90.38 | 29.5 |  | 0.46
| Total |  | 19008 | 6629.64 | 34.88% | 3781.366 | 6128.316 |  | 2468.678

## Summary 2A (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | PDN |  | 674 | 342.3 | 50.79% | 85 | 246.7
2 | CMB/ Sripalee Campus |  | 512 | 161.02 | 31.45% | 78.95 | 272.03
3 | SJP |  | 2006 | 490 | 24.43% | 175 | 1120
4 | KLN |  | 670 | 98.72 | 14.73% | 81.4 | 213
5 | MRT |  | 566 | 285.45 | 50.43% | 26 | 149
6 | UJA / Vavuniya Campus |  | 1605 | 684 | 42.62% | 105.1 | 572.9
7 | RUH |  | 945 | 393.56 | 41.65% | 551.44 | 0
8 | EUSL |  | 519 | 265 | 51.06% | 5 | 24
9 | RUSL |  | 737 | 240.01 | 32.57% | 140 | 283
10 | SUSL |  | 540 | 11.16 | 2.067% | 90.64 | 147.36
11 | SEUSL |  | 210 | 23.04 | 10.97% | 126.96 | 60
12 | WUSL |  | 850.31 | 172.8 | 20.32% | 100.1 | 369.21
13 | UVPA |  | 250 | 109.65 | 43.86% | 56 | 84.35
14 | UWU |  | 551.77 | 76.2 | 13.81% | 27.603 | 78.863
15 | Trinco |  | 419 | 303.13 | 72.35% | 67.8 | 48.07
16 | PGIM |  | 420 | 59 | 14.05% | 153 | 145.6
17 | PGIPBS |  | 500 | 0 | 0% | 0 | 0
18 | IIM |  | 0 | 0 | - | 0 | 0
19 | GWAI |  | 104 | 28.64 | 27.54% | 75.36 | 0
| Total |  | 12079.08 | 3743.68 | 30.99% | 1945.353 | 3814.083

## Summary3 (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 3 | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | PDN |  | 589 | 287.78 | 48.86% | 73.06 | 177.47
2 | CMB/ Sripalee Campus |  | 275 | 141.99 | 51.63% | 64 | 69.01
3 | SJP |  | 615 | 327 | 53.17% | 72 | 237
4 | KLN |  | 581 | 203.72 | 35.06% | 119.19 | 139.04
5 | MRT |  | 979 | 530.58 | 54.2% | 287 | 161.42
6 | UJA / Vavuniya Campus |  | 812 | 167.2 | 20.59% | 2 | 877.3
7 | RUH |  | 464 | 199.8 | 43.06% | 245.27 | 20
8 | EUSL |  | 234 | 171.3 | 73.21% | 29 | 27.2
9 | RUSL |  | 410 | 147.97 | 36.09% | 240 | 13
10 | SUSL |  | 330 | 95.1 | 28.82% | 176.27 | 58.63
11 | SEUSL |  | 492 | 142.47 | 28.96% | 221.84 | 127.69
12 | WUSL |  | 365.69 | 231.88 | 63.41% | 80 | 50.12
13 | UVPA |  | 171 | 72.98 | 42.68% | 56 | 41.62
14 | UWU |  | 273.23 | 84.38 | 30.88% | 107.193 | 107.193
15 | Trinco |  | 96 | 15.25 | 15.89% | 29.55 | 51.2
16 | PGIM |  | 15 | 15 | 100% | 15 | 0
17 | PGIPBS |  | 10 | 1.84 | 18.4% | 3.62 | 4.54
18 | IIM |  | 157 | 34.7 | 22.1% | 0 | 122.3
19 | GWAI |  | 60 | 15.02 | 25.03% | 15.02 | 29.5
| Total |  | 6928.92 | 2885.96 | 41.65% | 1836.013 | 2314.233

## Adjusted Final (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3
HEI |  | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Required funds October - December 2016 | Reasons for slow progress (if any)
|  | Rs. Mn | Rs. Mn | % | Rs. Mn | Rs. Mn | Rs. Mn
|  | (a) | (b) | ( c) | (d) | (e) | (f)
(d) + ( e)
1 | PDN | 1263 | 630.08 | 49.8876 | 158.06 | 424.17 | 582.23 |  | 50.69
2 | CMB | 787 | 303.01 | 38.5019 | 142.95 | 341.04 | 483.99 |  | 0 | 445.96
3 | SJP | 2621 | 817 | 31.1713 | 247 | 1357 | 1604 |  | 200 | 0.56666
4 | KLN | 1251 | 302.44 | 24.1759 | 200.59 | 352.04 | 552.63 |  | 395.93 | 56.6658
5 | MRT | 1545 | 816.03 | 52.8175 | 313 | 310.42 | 623.42 |  | 105.55
6 | UJA | 2417 | 851.2 | 35.2172 | 107.1 | 1450.2 | 1557.3 |  | 8.5
7 | RUH | 1409 | 593.36 | 42.1121 | 796.71 | 20 | 816.71 |  | -1.07
8 | EUSL | 753 | 436.3 | 57.9416 | 34 | 51.2 | 85.2 |  | 231.5
9 | RUSL | 1147 | 387.98 | 33.8256 | 380 | 296 | 676 |  | 83.02
10 | SUSL | 870 | 106.26 | 12.2138 | 266.91 | 205.99 | 472.9 |  | 290.84
11 | SEUSL | 702 | 165.51 | 23.5769 | 348.8 | 187.69 | 536.49 |  | 0
12 | WUSL | 1216 | 404.68 | 33.2796 | 180.1 | 419.33 | 599.43 |  | 211.89
13 | UVPA | 421 | 182.63 | 43.38 | 112 | 125.97 | 237.97 |  | 0.4
14 | UWU | 825 | 160.58 | 19.4642 | 134.796 | 186.056 | 320.852 |  | 343.568
15 | Trinco | 515 | 318.38 | 61.8214 | 97.35 | 99.27 | 196.62 |  | 0
16 | PGIM | 435 | 74 | 17.0115 | 168 | 145.6 | 313.6 |  | 47.4
17 | PGIPBS | 510 | 1.84 | 0.36078 | 3.62 | 4.54 | 8.16 |  | 500
18 | IIM | 157 | 34.7 | 22.1019 | 0 | 122.3 | 122.3 |  | 0
19 | GWAI | 164 | 43.66 | 26.622 | 90.38 | 29.5 | 119.88 |  | 0.46
Total |  | 19008 | 6629.64 | 34.8782 | 3781.366 | 6128.316 | 9909.682 |  | 2468.678
Draft

## Summary Original (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3 | [8 empty] | Rs. Million
| HEI | Form | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 % | Committed Expenditure up to 30.09.2016 | with Committed Expenditure % | Target Expenditure October - December 2016 | With Target Expenditure % | Reasons for slow progress (if any)
1 | PDN |  | 1263 | 630.08 | 49.8876 | 199.06 | 65.6485 | 755.96 | 125.5028 |  | -322.1
2 | CMB |  | 787 | 303.01 | 38.5019 | 142.95 | 56.6658 | 341.04 | 100 |  | 0 | 445.96
3 | SJP |  | 2621 | 817 | 31.1713 | 247 | 40.5952 | 1358 | 92.4075 |  | 199 | 0.56666
4 | KLN |  | 1251 | 302.44 | 24.1759 | 200.59 | 40.2102 | 352.04 | 68.3509 |  | 395.93 | 56.6658
5 | MRT |  | 1545 | 816.03 | 52.8175 | 313 | 73.0764 | 310.42 | 93.1683 |  | 105.55
6 | UJA |  | 2417 | 851.2 | 35.2172 | 107.1 | 39.6483 | 1563.55 | 104.338 |  | -104.85
7 | RUH |  | 1409 | 593.36 | 42.1121 | 796.71 | 98.6565 | 713.37 | 149.286 |  | -694.44
8 | EUSL |  | 753 | 436.3 | 57.9416 | 34 | 62.4568 | 51.2 | 69.2563 |  | 231.5
9 | RUSL |  | 1147 | 387.97 | 33.8248 | 380 | 66.9547 | 522 | 112.4647 |  | -142.97
10 | SUSL |  | 870 | 106.26 | 12.2138 | 266.91 | 42.8931 | 472.9 | 97.2494 |  | 23.93
11 | SEUSL |  | 702 | 165.51 | 23.5769 | 348.8 | 73.2635 | 187.69 | 100 |  | 0
12 | WUSL |  | 1216 | 404.68 | 33.2796 | 180.1 | 48.0905 | 580.59 | 95.8363 |  | 50.63
13 | UVPA |  | 421 | 182.63 | 43.38 | 112 | 69.9834 | 125.97 | 99.905 |  | 0.4
14 | UWU |  | 825 | 160.58 | 19.4642 | 135 | 35.8279 | 186 | 58.3733 |  | 343.42
15 | Trinco |  | 515 | 318.38 | 61.8214 | 97.35 | 80.7243 | 99.27 | 100 |  | 0
16 | PGIM |  | 435 | 74 | 17.0115 | 168 | 55.6322 | 145.6 | 89.1034 |  | 47.4
17 | PGIPBS |  | 510 | 1.84 | 0.36078 | 3.62 | 1.0706 | 4.54 | 1.9608 |  | 500
18 | IIM |  | 157 | 34.7 | 22.1019 | 0 | 22.1019 | 122.3 | 100 |  | 0
19 | GWAI |  | 164 | 43.66 | 26.622 | 146.2 | 115.7683 | 87.5 | 169.122 |  | -113.36
Total |  |  | 19008 | 6629.63 | 34.8781 | 3878.39 | 55.2821 | 7979.94 | 97.2641 |  | 520.04

## PDN (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Peradeniya | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 674 | 427.3 | 63.4% |  | 246.7
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 25
| Sub Total |  | 699 | 427.3 | 61.13% | 0 | 246.7
5 | Rehabilitation & Improvement | 3 | 77 | 77 | 100%
6 | Acquisition of Fixed Assets |  | 372 | 259.36 | 69.72% |  | 112.64
7 | Human Capital Development Projects |  | 140 | 24.48 | 17.49% |  | 115.52 | Research proposal approved by the research Committee and funds received at the end of the June - 2016
| Sub Total |  | 589 | 360.84 | 61.26% | 0 | 228.16
| Total |  | 1288 | 788.14 | 61.19% | 0 | 474.86
Note I : Allocation for the year is insufficient to meet the essential requirements of the University and therefore additional funds Rs. 101 Mn for Rehabilitation & improvement and Rs. 271 Mn for Acquisition of Fixed Assets
………………………………..
Bursar

## CMB (hidden)
[8 empty] | Annex II | Copy & Typed
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Colombo | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 362 | 239.97 | 44% | 0 | 122.03 | Due to bad weather condition, construction works got delay
2 | Technology Stream |  | 150 | 0 | 0% | 0 | 150 | Procurements are in order & project starts in Oct & Dec 2016. Students will be admitted to the university in 2017/18.
3 | Establishment of Engineering Faculties - (Note I) |  | 0 | 0 | 0% | 0 | 0
4 | Staff Quarters - (Note I) |  |  | 0 | 0% | 0 | 0
| Sub Total |  | 512 | 239.97 | 46.87% | 0 | 272.03
5 | Rehabilitation & Improvement | 3 | 140 | 86.61 | 45% | 25.95 | 27.44 | Bills are not submitted & submitted bills are due for payments end of Dec. 2016. Utilization would be close to 100%
6 | Acquisition of Fixed Assets |  | 65 | 47.37 | 73% | 12 | 5.63
7 | Human Capital Development Projects |  | 70 | 32.064 | 46% | 2 | 35.936 | 3 months crash programme is underway.
| Sub Total |  | 275 | 166.044 | 60.38% | 39.95 | 69.006
| Total |  | 787 | 406.014 | 51.59% | 39.95 | 341.036
Note I : If relevant only
………………………………..
Bursar

## SJP (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Sri Jayewardenepura | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 12.10.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 631 | 464 | 73.53% | 113 | 240
2 | Technology Stream |  | 775 | 88 | 11.35% | 36 | 705 | Although the Faculty was expecting to receive a land by June,2016 for construction of the new building, the land was finally allocated to the University by the UDA only in September, 2016. Soil investigations has already been done and the Bidding Document for construction work is almost complete and will be submitted for approval of the MPC in October 2016. Thereafter, other activities can be commenced as scheduled and mobilization advance can be made December, 2016 or Mid January 2017.
3 | Establishment of Engineering Faculties - (Note I) |  | 600 | 13 | 2.167% | 25 | 175 | Land was allocated to the Faculty on 22nd September 2016 & contour survey soil investigation has been done.
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 2006 | 565 | 28.17% | 174 | 1120
5 | Rehabilitation & Improvement | 3 | 150 | 79 | 52.67% | 22 | 68 | Almost completed
6 | Acquisition of Fixed Assets |  | 170 | 69 | 40.59% | 26 | 95 | Almost completed
7 | Human Capital Development Projects |  | 20 | 1.6 | 8% | 1.32 | 3 | As the amount allocated for Rehabilitation & Acquisition of fixed assets were not sufficient, it is intended to utilize the allocation in the Human capital & strengthening Research for Rehabilitation & acquisition of fixed assets . Therefore Human capital development fund & Strengthening Research fund will be transferred to Rehabilitation & Acquisition of Fixed Assets vote.
| Strengthening Research |  | 200 | 56.29 | 28.14% | 18.823 | 46.2
| University Township Project |  | 75 | 45.78 | 61.04% | 4.45 | 24.92 | Almost completed
| Sub Total |  | 615 | 251.67 | 40.92% | 72.593 | 237.12
| Total |  | 2621 | 816.67 | 31.16% | 246.593 | 1357.12
Note I : If relevant only
………………………………..
Bursar

## KLN (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Kelaniya | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 450 | 93.96 | 20.88% | 71.49 | 143 | Bills have not been presented. Vouchers are being processed for payments.
2 | Technology Stream |  | 220 | 4.76 | 2.164% | 9.91 | 70 | Acquisition & curriculum development are in progress. Quotation has been called for temporary location with 35000 sq.ft. Govt. valuation is 1.5 Mn, Quoted price 4.1 Mn.
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 670 | 98.72 | 14.73% | 81.4 | 213
5 | Rehabilitation & Improvement | 3 | 195.92 | 75.86 | 38.72% | 50.55 | 43.34 | Rehabilitation works & Acquisition are in the process. Bills for concluded activities are being processed for payment.
6 | Acquisition of Fixed Assets |  | 280.08 | 108.23 | 38.64% | 68.65 | 68.45
7 | Human Capital Development Projects |  | 105 | 19.63 | 18.7% | 0 | 27.25
| Sub Total |  | 581 | 203.72 | 35.06% | 119.2 | 139.04
| Total |  | 1251 | 302.44 | 24.18% | 200.6 | 352.04
Note I : If relevant only
………………………………..
Bursar

## MRT (hidden)
[8 empty] | Annex II | Typed
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Moratuwa | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 566 | 285.45 | 50.43% | 26 | 149 | There were some savings on contracts due to changes & some contracts are in design stage
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 566 | 285.45 | 50.43% | 26 | 149
5 | Rehabilitation & Improvement | 3 | 75 | 61.74 | 82.32% | 4 | 9.26
6 | Acquisition of Fixed Assets |  | 821 | 449.4 | 54.74% | 271 | 100.6
7 | Human Capital Development Projects |  | 83 | 19.44 | 23.42% | 12 | 51.56 | Funds have been allocated to international conferences. Most of the conferences will be held during the months of November & December 2016
| Sub Total |  | 979 | 530.58 | 54.2% | 287 | 161.42
| Total |  | 1545 | 816.03 | 52.82% | 313 | 310.42
Note I : If relevant only
………………………………..
Bursar

## RUH (hidden)
[8 empty] | Annex II | Copy & typed
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Ruhuna | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 585 | 342.88 | 58.61% | 242.12 | 0 | * Township Project (Rs. 130.0 Mn.)
2 | Technology Stream |  | 310 | 50.68 | 16.35% | 139.32 | 120 | Procurement has completed. Pending letter of award by MOHE. Construction will be commenced on 2nd November 2016.
3 | Establishment of Engineering Faculties - (Note I) |  | 0 | 0 |  | 0 | 0
4 | Staff Quarters - (Note I) |  | 50 | 0 | 0% | 10 | 40 | Contract awarded on 10/08/2016 and physical progress is 30% at this stage.
| Sub Total |  | 945 | 393.56 | 41.65% | 391.44 | 160
5 | Rehabilitation & Improvement | 3 | 92 | 67.71 | 73.6% | 24.29 | 0
6 | Acquisition of Fixed Assets |  | 310 | 132.04 | 42.59% | 177.96 | 0
7 | Human Capital Development Projects |  | 62 | 0.05 | 0.08065% | 43.02 | 20 | Two years duration for the course of studies.
| Sub Total |  | 464 | 199.8 | 43.06% | 245.27 | 20
| Total |  | 1409 | 593.36 | 42.11% | 636.71 | 180
Note I : If relevant only
* Contract signed with UDA in September and expect the payment for mobilization advance and consultancy charges.
Bursar
07.10.2016

## UJA (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of Jaffna | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 480 | 370 | 77.08% | 40.1 | 69.9 |  | Eng. Faculty Rs. 300mn includes
2 | Technology Stream |  | 475 | 10 | 2.105% | 0 | 222 | Kilinochchi - Procurements are in process and bid documents are ready for advertising (CATB)
Vavuniya - Pre Tech. completed and documents handed over to MOHE due for advertising
3 | Establishment of Engineering Faculties - (Note I) |  | 600 | 304 | 50.67% | 112.9 | 231 | Rs. 65 million paid on 06.10.2016
4 | Staff Quarters - (Note I) |  | 50 | 0 | 0% |  | 50 | Project has been given to buildings department they have started the work
| Sub Total |  | 1605 | 684 | 42.62% | 153 | 572.9
5 | Rehabilitation & Improvement | 3 | 405 | 93.7 | 23.14% | 2 | 240 | Procurement completed. Bills are to be received for payments
6 | Acquisition of Fixed Assets |  | 351 | 67.8 | 19.32% | 0 | 587 |  | 80
7 | Human Capital Development Projects |  | 56 | 5.7 | 10.18% | 0 | 50.3
| Sub Total |  | 812 | 167.2 | 20.59% | 2 | 877.3
| Total |  | 2417 | 851.2 | 35.22% | 155 | 1450.2
Note I : If relevant only
………………………………..
Bursar

## OUSL (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Open University of Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 25
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 25 | 0
5 | Rehabilitation of & Improvement | 3 | 18
6 | Acquisition of Fixed Assets |  | 57
7 | Human Capital Development Projects |  | 30
| Sub Total |  | 105 | 0
| Total |  | 130 | 0
Note I : If relevant only
………………………………..
Bursar

## EUSL (hidden)
[8 empty] | Annex II | Copy
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Eastern University, Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 369 | 250 | 67.75% | 0 | 19 | Building for Agri Faculty 100 Mn: In awarding stage
2 | Technology Stream |  | 125 | 15 | 12% | 5 | 5 | Construction of building 100Mn: In preparation of Bid documents
3 | Establishment of Engineering Faculties - (Note I) |  | 0 | 0
4 | Staff Quarters - (Note I) |  | 25 | 0 | 0% | 0 | 0 | In the process of preparing bid document
| Sub Total |  | 519 | 265 | 51.06% | 5 | 24
5 | Rehabilitation & Improvement | 3 | 82 | 71.5 | 87.2% | 10 | 0.5
6 | Acquisition of Fixed Assets |  | 88 | 85.3 | 96.93% | 1 | 1.7
7 | Human Capital Development Projects |  | 64 | 14.5 | 22.66% | 18 | 25
| Sub Total |  | 234 | 171.3 | 73.21% | 29 | 27.2
| Total |  | 753 | 436.3 | 57.94% | 34 | 51.2
Note I : If relevant only
………………………………..
Bursar

## Trinco (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Trincomalee Campus | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 394 | 303.13 | 76.94% | 67.8 | 23.07
2 | Technology Stream |  | 0 | 0 | - | 0 | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0 | 0 | - | 0 | 0
4 | Staff Quarters - (Note I) |  | 25 | 0 | - | 0 | 25 | Procurement process in progress
| Sub Total |  | 419 | 303.13 | 72.35% | 67.8 | 48.07
5 | Rehabilitation & Improvement | 3 | 55 | 8.94 | 16.25% | 8.3 | 37.76
6 | Acquisition of Fixed Assets |  | 31.5 | 5.11 | 16.22% | 19.75 | 6.64
7 | Human Capital Development Projects |  | 9.5 | 1.2 | 12.63% | 1.5 | 6.8
| Sub Total |  | 96 | 15.25 | 15.89% | 29.55 | 51.2
| Total |  | 515 | 318.38 | 61.82% | 97.35 | 99.27
Note I : If relevant only
………………………………..
Bursar

## RUSL (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Rajarata University of Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 357 | 218.49 | 61.2% | 40 | 55 | Pending Cabinet decisions
2 | Technology Stream |  | 330 | 21.52 | 6.521% | 100 | 208.48 | Building - TEC report with the recommendations submitted to MOHE
Equipment - Procurement are in process and part of the equipment will be delivered in December 2016.
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 50 |  | 0% |  | 20 | In the bidding process (Technology staff quarters)
| Sub Total |  | 737 | 240.01 | 32.57% | 140 | 283.48
5 | Rehabilitation & Improvement | 3 | 85 | 82.3 | 96.82% | 2.4 | 0 | Additional funds required Rs. 20 Mn (Main Entrance Rs.15 Mn & Farm Managers Office Rs.5 Mn)
6 | I Acquisition of Fixed Assets |  | 60 | 56.18 | 93.63% | 5.6 | 0 | To be awarded Hostel Furniture
| II Acquisition of 9 acre land at Puliyankulama for Faculty of Agriculture |  | 230 | 0 | 0% | 230 | 0 | Pending Cabinet decision
7 | Human Capital Development Projects |  | 35 | 9.49 | 27.11% | 2 | 13
| Sub Total |  | 410 | 147.97 | 36.09% | 240 | 13
| Total |  | 1147 | 387.98 | 33.83% | 380 | 296.48
Note I : If relevant only
|  |  | 817 |  |  |  |  | ………………………………..
|  |  | 947 |  |  |  |  | Bursar
1147
1147

## SUSL (hidden)
[8 empty] | Annex II | Copy & Typed
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Sabaragamuwa University of Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 255 | 11.1 | 4.353% | 90.64 | 83.36 | Geomatic building is re-tendered as advised by MOHE.
2 | Technology Stream |  | 275 | 0.06 | 0.02182% | 0 | 54 | Location has been changed
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 10 | 0 |  |  | 10 | Procurement process is in progress.
| Sub Total |  | 540 | 11.16 | 2.067% | 90.64 | 147.36
5 | Rehabilitation & Improvement | 3 | 83 | 21.6 | 26.02% | 39.17 | 22.23 | Pending bills to be settled.
6 | Acquisition of Fixed Assets |  | 200 | 64 | 32% | 116 | 20 | Procurement has completed. Bills are pending for payments.
7 | Human Capital Development Projects |  | 47 | 9.5 | 20.21% | 21.1 | 16.4 | Most of Applications received in Sep.2016
| Sub Total |  | 330 | 95.1 | 28.82% | 176.27 | 58.63
| Total |  | 870 | 106.26 | 12.21% | 266.91 | 205.99
Note I : If relevant only
………………………………..
Bursar

## SEUSL (hidden)
[8 empty] | Annex II | Typed
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : South Eastern University of Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 50 | 23.04 | 46.08% | 26.96 | 0 | The procurement works are being processed. Therefore the balance will be utilized accordingly.
2 | Technology Stream |  | 160 | 0 | 0% | 100 | 60 | This fund allocation had been received to the Faculty of Information Technology on July 2016 and the procurement works are being processed. Therefore the balance will be utilized accordingly.
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 210 | 23.04 | 10.97% | 126.96 | 60
5 | Rehabilitation & Improvement | 3 | 45 | 30 | 66.67% | 15 | 0
6 | Acquisition of Fixed Assets |  | 416 | 259.16 | 62.3% | 56.84 | 100 | This is an especial allocation for the faculty of Engineering RS.100Mn received on July 2016. Since the procurement works are being processed. The balance funds will be utilized accordingly.
7 | Human Capital Development Projects |  | 31 | 3.31 | 10.68% | 0 | 27.69
| Sub Total |  | 492 | 292.47 | 59.45% | 71.84 | 127.69
| Total |  | 702 | 315.51 | 44.94% | 198.8 | 187.69
Note I : If relevant only
………………………………..
Bursar

## WUSL (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Wayamba University of Sri Lanka | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 370.31 | 155.1 | 41.88% | 72 | 143.21 | Bills are pending for payments
2 | Technology Stream |  | 430 | 17.7 | 4.116% | 28.1 | 226 | TEC reports of Agriculture stage III & Tech Stream building forwarded to SCAPC & waiting for Cabinet approval
3 | Establishment of Faculty of Medicine- (Note I) |  | 200
4 | Staff Quarters - (Note I) |  | 50 |  | 0% |  |  | Contract awarded on 5th Oct 2016 & due to be completed in March 2017
| Sub Total |  | 1050.31 | 172.8 | 16.45% | 100.1 | 369.21
5 | Rehabilitation & Improvement | 3 | 35.19 | 29.81 | 84.71% | 0 | 5.38
6 | Acquisition of Fixed Assets |  | 280 | 190.26 | 67.95% | 80 | 9.74
7 | Human Capital Development Projects |  | 50.5 | 11.81 | 23.39% | 0 | 35
| Sub Total |  | 365.69 | 231.88 | 63.41% | 80 | 50.12
| Total |  | 1416 | 404.68 | 28.58% | 180.1 | 419.33
Note I : If relevant only
………………………………..
Bursar

## UVPA (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : University of the Visual & Performing Arts | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 250 | 109.65 | 43.86% | 56 | 84.35 | Delaying submitting bills
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 250 | 109.65 | 43.86% | 56 | 84.35
5 | Rehabilitation & Improvement | 3 | 35 | 23.59 | 67.4% | 5 | 6 | Delaying submitting bills
6 | Acquisition of Fixed Assets |  | 111.375 | 46.82 | 42.04% | 43 | 21.56 | Equipment have been received but due to construction delays they are not fixed. Therefore bills have not been paid yet.
7 | Human Capital Development Projects |  | 24.625 | 2.57 | 10.44% | 8 | 14.06 | Programmes have been planned by the 3 faculties during last 3 months.
| Sub Total |  | 171 | 72.98 | 42.68% | 56 | 41.62
| Total |  | 421 | 182.63 | 43.38% | 112 | 125.97
Note I : If relevant only
………………………………..
Bursar

## annex i
[9 empty] | Annex I | Typed
Progress Review on Budget Proposals -2016
University ……………………………………….. | [8 empty] | Rs. Million
| Item | Allocation 2016 | Expenditure up to 31.12.2016 | Physical Progress (%) | Target for 2017 |  |  |  | Current Status
[5 empty] | Q1 | Q2 | Q3 | Q4
1 | Establishment of Faculties of Technology
Rehabilitation Works
Acquisitions
Others
2 | Staff Quarters
3 | Engineering Faculty - Kilinochchi
4 | New - Faculty of Medicine - WUSL
5 | Encourage accreditation with profession bodies of international repute

## Total (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Summary Universities & Trinco | [5 empty] | Rs. Million
| Item | Form | Allocation 2016 | Expenditure up to 30.09.2016 | % | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 5818.31
2 | Technology Stream |  | 3250
3 | Establishment of Engineering Faculties - (Note I) |  | 1400
4 | Staff Quarters - (Note I) |  | 285
| Sub Total |  | 10753.31 | 0
5 | Rehabilitation of & Improvement | 3 | 1573.11
6 | Acquisition of Fixed Assets |  | 3612.955
7 | Human Capital Development Projects |  | #REF!
| Sub Total |  | #REF! | 0
| Total |  | #REF! | 0
Note I : If relevant only
………………………………..
Bursar

## PGIM (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Postgraduate Institute of Medicine | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 420 | 59 | 14.05% | 153 | 145.6 | Due to delay in obtaining CMC clearance for building design
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 420 | 59 | 14.05% | 153 | 145.6
5 | Rehabilitation & Improvement | 3 | 7 | 7 | 100% | 7
6 | Acquisition of Fixed Assets |  | 8 | 8 | 100% | 8
7 | Human Capital Development Projects |  | 0
| Sub Total |  | 15 | 15 | 100% | 15 | 0
| Total |  | 435 | 74 | 17.01% | 168 | 145.6
Note I : If relevant only
………………………………..
Bursar

## PBS (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Postgraduate Institute of Pali & Buddhist Studies | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Infrastructure for PGIPBS | 2 - A | 0 | 0 |  | 0 | 0 | Land matter was not settled. Delay the project
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 0 | 0 | #DIV/0! | 0 | 0
5 | Rehabilitation & Improvement | 3 | 0.2 | 0.2 | 100% | 0 | 0
6 | Acquisition of Fixed Assets |  | 7.2 | 1.44 | 20% | 2.86 | 2.9
7 | Human Capital Development Projects |  | 2.6 | 0.2 | 7.692% | 0.755 | 1.64
| Sub Total |  | 10 | 1.84 | 18.4% | 3.615 | 4.54
| Total |  | 10 | 1.84 | 18.4% | 3.615 | 4.54
Note I : If relevant only
………………………………..
Bursar

## IIM (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Institute of Indigenous Medicine | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 0
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 0 | 0 |  | 0 | 0
5 | Rehabilitation & Improvement | 3 | 23 | 21.6 | 93.91% | 0 | 1.4
6 | Acquisition of Fixed Assets |  | 123.5 | 11 | 8.907% | 0 | 112.5 | Land will be purchased in October (Rs. 101.0 Mn)
7 | Human Capital Development Projects |  | 10.5 | 2.1 | 20% | 0 | 8.4 | International Conference will be held in December (Rs. 4.6 Mn)
| Sub Total |  | 157 | 34.7 | 22.1% | 0 | 122.3
| Total |  | 157 | 34.7 | 22.1% | 0 | 122.3
Note I : If relevant only
………………………………..
Bursar

## GWAI (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI : Gampaha Wickramarachchi Ayurveda Institute | [7 empty] | Rs. Million
| Item | Form | Allocation 2016 (including Supplementary Allocation) | Expenditure up to 30.09.2016 | % | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Reasons for slow progress (if any)
1 | Construction Projects | 2 - A | 104 | 28.64 | 27.54% | 75.36
2 | Technology Stream |  | 0
3 | Establishment of Engineering Faculties - (Note I) |  | 0
4 | Staff Quarters - (Note I) |  | 0
| Sub Total |  | 104 | 28.64 | 27.54% | 75.36 | 0
5 | Rehabilitation & Improvement | 3 | 15 | 7.06 | 47.07% | 7.06 | 0
6 | Acquisition of Fixed Assets |  | 41 | 7.96 | 19.41% | 7.96 | 29
7 | Human Capital Development Projects |  | 4 | 0 | 0% | 0 | 0.5
| Sub Total |  | 60 | 15.02 | 25.03% | 15.02 | 29.5
| Total |  | 164 | 43.66 | 26.62% | 90.38 | 29.5
Note I : If relevant only
………………………………..
Bursar

## Released (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
Summary - Form 2 - A & 3
HEI |  | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Required funds October - December 2016 | Reasons for slow progress (if any)
|  | Rs. Mn | Rs. Mn | % | Rs. Mn | Rs. Mn | Rs. Mn |  |  | 6550 | 31000 | 150
|  | (a) | (b) | ( c) | (d) | (e) | (f) |  |  | 4125 | 6600 | 775
[7 empty] | (d) + ( e) |  |  | 6450 | 116600 | 220
1 | PDN | 1288 | 787 | 61.1025 | 158.06 | 424.17 | 582.23 |  | -81.23 | 2300 | 53565 | 475
2 | CMB | 787 | 406 | 51.5883 | 142.95 | 341.04 | 483.99 |  | -102.99 | 25000 | 4150 | 310
3 | SJP | 2021 | 796.2 | 39.3963 | 247 | 1357 | 1604 |  | -379.2 | 3250 | 3600 | 125
4 | KLN | 1251 | 358.67 | 28.6707 | 200.59 | 352.04 | 552.63 |  | 339.7 | 47675 | 14820 | 330
5 | MRT | 1545 | 878.5 | 56.8608 | 313 | 310.42 | 623.42 |  | 43.08 |  | 41800 | 275
6 | UJA | 2417 | 606 | 25.0724 | 107.1 | 1450.2 | 1557.3 |  | 253.7 |  | 36760 | 160
7 | RUH | 1409 | 585 | 41.5188 | 636.71 | 180 | 816.71 |  | 7.29 |  | 3888 | 430
8 | OUSL | 230 | 64.65 | 28.1087 | [6 empty] | 312783 | 250
9 | EUSL | 753 | 436 | 57.9017 | 34 | 51.2 | 85.2 |  | 231.8 |  |  | 3500
10 | RUSL | 1147 | 432.5 | 37.7071 | 380 | 296 | 676 |  | 38.5
11 | SUSL | 870 | 130 | 14.9425 | 266.91 | 205.99 | 472.9 |  | 267.1
12 | SEUSL | 702 | 370 | 52.7066 | 348.8 | 187.69 | 536.49 |  | -204.49
13 | WUSL | 1216 | 400.25 | 32.9153 | 180.1 | 419.33 | 599.43 |  | 216.32
14 | UVPA | 421 | 166 | 39.4299 | 112 | 125.97 | 237.97 |  | 17.03
15 | UWU | 800 | 192.7 | 24.0875 | 134.796 | 186.056 | 320.852 |  | 286.448
16 | Trinco | 515 | 328 | 63.6893 | 97.35 | 99.27 | 196.62 |  | -9.62
17 | Other Postgraduate Institutes | 73 | 47.675 | 65.3082
18 | Other Higher Educational Institutes | 730 | 312.78 | 42.8466
19 | PGIM | 435 | 128 | 29.4253 | 168 | 145.6 | 313.6 |  | -6.6
20 | UGC | 1032 | 37.3 | 3.6143 |  |  |  |  | 994.7 |  | 100.225
Total |  | 19642 | 7463.225 | 37.9963 | 3527.366 | 6131.976 | 9659.342 |  | 2519.433
Innitial Allocation |  | 15942
Technology Stream |  | 3000
Establishment of Engineering Faculties |  | 400
Staff Quarters |  | 300
Total Allocation |  | 19642
Note on D5: Author: Actual released

## Released final (hidden)
Annex II
Summary - Financial Progress on Capital Projects as at 30.09.2016
(Refer: National Budget Circular No. 06/2015)
HEI |  | Allocation 2016 | Expenditure up to 30.09.2016 | Utilization up to 30/09/2016 | Committed Expenditure up to 30.09.2016 | Target Expenditure October - December 2016 | Required funds October - December 2016 | Reasons for slow progress (if any) |  | Allocation 2016 with Technology Rs.3,000mn | Technology Rs.3,000Mn | Allocation without Technology Rs.3,000Mn
|  | Rs. Mn | Rs. Mn | % | Rs. Mn | Rs. Mn | Rs. Mn |  |  | Rs. Mn | Rs. Mn | Rs. Mn
|  | (a) | (b) | ( c) | (d) | (e) | (f) |  |  | (a) | (a) | (a)
(d) + ( e)
1 | PDN | 1288 | 787 | 61.1025 | 158.06 | 424.17 | 582.23 |  | -81.23 | 1288 | 0 | 1288
2 | CMB | 637 | 406 | 63.7363 | 142.95 | 341.04 | 483.99 |  | -252.99 | 787 | 150 | 637
3 | SJP | 1321 | 683.2 | 51.7184 | 211 | 652 | 863 |  | -225.2 | 2021 | 700 | 1321
4 | KLN | 1081 | 353.91 | 32.7391 | 190.68 | 282.04 | 472.72 |  | 254.37 | 1251 | 170 | 1081
5 | MRT | 1545 | 878.5 | 56.8608 | 313 | 310.42 | 623.42 |  | 43.08 | 1545 | 0 | 1545
6 | UJA | 2017 | 996 | 49.3803 | 107.1 | 1228.2 | 1335.3 |  | -314.3 | 2417 | 400 | 2017
7 | RUH | 1149 | 534.32 | 46.503 | 497.39 | 60 | 557.39 |  | 57.29 | 1409 | 260 | 1149
8 | OUSL | 230 | 64.65 | 28.1087 | [5 empty] | 230 | 0 | 230
9 | EUSL | 653 | 421 | 64.4717 | 29 | 46.2 | 75.2 |  | 156.8 | 753 | 100 | 653
10 | RUSL | 867 | 410.98 | 47.4025 | 280 | 87.52 | 367.52 |  | 88.5 | 1147 | 280 | 867
11 | SUSL | 645 | 129.94 | 20.1457 | 266.91 | 151.99 | 418.9 |  | 96.16 | 870 | 225 | 645
12 | SEUSL | 567 | 370 | 65.2557 | 248.8 | 127.69 | 376.49 |  | -179.49 | 702 | 135 | 567
13 | WUSL | 836 | 382.55 | 45.7596 | 152 | 193.33 | 345.33 |  | 108.12 | 1216 | 380 | 836
14 | UVPA | 421 | 166 | 39.4299 | 112 | 125.97 | 237.97 |  | 17.03 | 421 | 0 | 421
15 | UWU | 600 | 181.28 | 30.2133 | 106.796 | 107.056 | 213.852 |  | 204.868 | 800 | 200 | 600
16 | Trinco | 515 | 328 | 63.6893 | 97.35 | 99.27 | 196.62 |  | -9.62 | 515 | 0 | 515
17 | Other Postgraduate Institutes | 73 | 47.675 | 65.3082 |  |  | 0 |  |  | 73 | 0 | 73
18 | Other Higher Educational Institutes | 730 | 312.78 | 42.8466 |  |  | 0 |  |  | 730 | 0 | 730
19 | PGIM | 435 | 128 | 29.4253 | 168 | 145.6 | 313.6 |  | -6.6 | 435 | 0 | 435
20 | UGC | 1032 | 124.3 | 12.0446 |  |  | 0 |  | 907.7 | 1032 | 0 | 1032
| Technology Stream | 3000 | 444 | 14.8 | 446 | 1750 | 2196
Total |  | 19642 | 8150.085 | 41.4932 | 3527.036 | 6132.496 | 9659.532 |  | 1832.383 | 19642 | 3000 | 16642
Innitial Allocation |  | 15942 | [7 empty] | 15942 | 15942 | 15942
Technology Stream |  | 3000 | [7 empty] | 3000 | 3000 | 3000
Establishment of Engineering Faculties |  | 400 | [7 empty] | 400 | 400 | 400
Staff Quarters |  | 300 | [7 empty] | 300 | 300 | 300
Total Allocation |  | 19642 | [7 empty] | 19642 | 19642 | 19642
Note on D5: Author: Actual released